## Sheet1
Vendor | Issue | Severity | Action Required | Owner | Due Date | Status
CloudDocs Pro | Missing assurance report | Medium | Request SOC 2 report | IT | 2026-05-15 | Open
PayFlow HR | No evidence of annual penetration testing | High | Request security testing evidence | HR | 2026-05-10 | Open
PayFlow HR | Contract lacks clear security obligations | High | Update contract language | Legal | 2026-05-20 | Open
AlertStack | Annual review pending | Low | Schedule reassessment | Security | 2026-01-06 | Open